## W2
Stories | Tasks | Assignees | Estimated time | Time spent | Done | Notes
User must be able to create a user profile | Create user upon registration | Joyce Sung | 1h | 3h | Yes | First attempted from authentication service, later decided to keep function isolated in user microservice
Users must be able to edit their user details | Refactor the user update endpoint to have logic in the user service | Joyce Sung | 1h | 1h | Yes
Users should be able to edit their own activity | New start time of activity can't be before current time | Joyce Sung | 1h | 1h | In review
| Tests for update activity functionality and endpoint | Joyce Sung | 2h | 3h | In review
| Users are removed from an activity if the new time does not match their availability | Joyce Sung | 2h | 3h | In review
User can kick out participants from an activity they created | Kick an user from an activity | Alexandru Gabriel Cojocaru
Users must be able to sign up for an activity | Sign up an user for an activity | Alexandru Gabriel Cojocaru | 8 | 9 | Yes
An activity owner should be able to accept or decline a sign up. | Accept a user to an activity | Efe Unluyurt
| Create an email sending functionality using the library. | Efe Unluyurt
Users could only be able to sign up for a cox position if they have a suitable certificate. | Reject an applicant | Efe Unluyurt
| Get all participants | Efe Unluyurt
Users could be notified if they have been rejected for a certain activity. | Create activity controller tests | Khalit Gulamov | 4h | 5h | Yes
| Create activity domain tests | Khalit Gulamov |  |  | Yes
Users should be able to edit their own activity. | Delete an activity | Bogdan Bancuta | 1h | 1h | Yes
Users must be able to enter their certificates. | Create certificates class and cox certificate class |  | 2h | 5h | In progress
| Fix the integration tests for the notification microservice |  | 1h | 1h | In progress
Users could be notified if they have been rejected for a certain activity. | Connect kafka producer to the notification Kafka strategy | Alexandru-Nicolae Ojica | 7h | 8h | Done
| Integration testing | Alexandru-Nicolae Ojica | 5h | 2h | Done
| Fix the integration tests for the notification microservice | Alexandru-Nicolae Ojica | 3h | 13h | Done

## Template
Stories | Tasks | Assignees | Estimated time | Spent time | Done | Notes