## W2
Stories | Tasks | Assignees | Estimated time | Time spent | Done | Notes
Users must be able to create and update their user details | Additional tests update user endpoint | Joyce Sung | 2h | 2h | Yes
Users should be able to edit their own activity | Create basic edit activity endpoint | Joyce Sung | 1h | 1h | In review
| Add location attribute to activity | Joyce Sung | 1h | 1h30 | In review
Create matching DTO and repository
Users must be able to sign up for an activity | Refactor activity structure | Alexandru Gabriel Cojocaru | 4h | 3h | Yes
Users must be able to sign up for an activity | Make the Return Activity List endpoint remove expired activties | Efe Unluyurt
Create an email sending functionality using the library.
Users could be notified if they have been rejected for a certain activity. | Add additional notification status for when activity is full + tests | Khalit Gulamov | 3h | 3h | Yes
| Add additional notification status for when activity is changed + tests | Khalit Gulamov |  |  | Yes
Users should be able to edit their own activity. | Delete an activity | Bogdan Bancuta | 1h | 1h | Yes
Users must be able to enter their certificates. | Create certificates class and cox certificate class |  | 2h | 5h | In progress
| Refactor how certificates are stored in user class and database |  | 1h | 1h | In progress
Users could be notified if they have been rejected for a certain activity. | Implement the strategy design pattern to facilitate the use of email and kafka strategies | Alexandru-Nicolae Ojica | 5h | 6h | Done
| Implement the email sending strategy | Alexandru-Nicolae Ojica | 2h | 1h | Done
| Fix the integration tests for the notification microservice | Alexandru-Nicolae Ojica | 3h | 7h | Done

## Template
Stories | Tasks | Assignees | Estimated time | Spent time | Done | Notes