## W2
Stories | Tasks | Assignees | Estimated time | Time spent | Done | Notes
Users must be able to specify the positions they can fill | Create template for User microservice | Bogdan Bancuta | 4h | 4h | Yes | Better renaming module
| Create class diagram for User microservice | Joyce Sung
Create repository for users
Users must be able to create activities | Create class design for Activity microservice | Alexandru Gabriel Cojocaru | 4h | 3h | In review | Design needs to be improved in future developments
| Create respository for activities | Efe Unluyurt
Create class diagram
Users could be notified if they have been rejected for a certain activity. | Create a template for Notification microservice | Khalit Gulamov | 3h | 4h | In review
Create repository for notifications
Create class diagram
Users must be logged in to be able to use the application | Create the repository to store user credentials. | Alexandru-Nicolae Ojica | 1h | 2h | In Review | I had to understand how the project and authentication works in order to make the database persistent
| Create the structure, make sure to use spring security. |  | 2h | 2h | In Review | The structure was already included in the template but I had to understand ho it works
| Create the class diagram.(upload it in the merge req) |  | 1h | 5m | In Review | Intellij has the option to generate class diagrams so I just did that
| Research Spring Security and how it applies to microservices |  | 4h | 6h | In Review | I watched tutorials on youtube to understand how spring security works

## Template
Stories | Tasks | Assignees | Estimated time | Spent time | Done | Notes