## W2
Stories | Tasks | Assignees | Estimated time | Time spent | Done | Notes
Users must be able to create and update their user details | Create user get endpoint | Joyce Sung | 1h | 1h | In review
| Create user update endpoint | Joyce Sung | 4h | 4h | In review
| test the newly created endpoints | Joyce Sung | 2h | 2h | In review
Users must be able to create activities | Create an activity | Alexandru Gabriel Cojocaru | 4h | 3h | Yes
Users must be able to sign up for an activity | Return activity list | Efe Unluyurt
Write tests for endpoints
Users could be notified if they have been rejected for a certain activity. | Create an email sending functionality using the library. | Khalit Gulamov | 3h | 4h | Yes
| Create tests for the email sending functionality. | Khalit Gulamov |  |  | Yes
| Create an endpoint inside notification microservice that sends an email | Alexandru-Nicolae Ojica | 3h | 3h | Yes
| Test the newly created endpoint | Alexandru-Nicolae Ojica | 2h | 1.5h | Yes
Users must be able to edit their availability | Create endpoint to add availability | Bogdan Bancuta | 5h | 10h | In testing | Problems with database persistency and representation appeared
| Create endpoint to remove availability |  |  |  | In testing
| Create endpoint to edit availability |  |  |  | In testing
| Refactor Availability Intervals class |  |  |  | Yes
The system should be scalable and reliable | Deploy kafka somewhere | Alexandru-Nicolae Ojica | 2h | 3h | Yes | I had to deploy kafka in gcp because my pc didn't have enough memory
| Implement a template for producers and consumers | Alexandru-Nicolae Ojica | 5h | 7h | Yes | A template is now implemented on the kafka-testing branch

## Template
Stories | Tasks | Assignees | Estimated time | Spent time | Done | Notes